## Cronograma_Projecto
Cronograma do Projeto IPCA GYM
Setembro | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex
|  |  | Apresentação da ideia | Inicialização do documento (contextualização) |  |  |  | Levantamento de requisitos
Outubro | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui
Validação de requisitos e prototipagem
| 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua
|  |  |  | Dossier de organização do grupo |  | Cronograma |  | Entrega 1 |  |  |  |  | Casos de uso
| 27 | 28 | 29 | 30 | 31
| Qui | Sex | Sáb | Dom | Seg
Casos de uso
Novembro | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom
Diagrama ER
| 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua
|  |  | Dossier de organização do grupo |  | Entrega 2 |  |  |  |  | Diagrama de atividades |  |  | Diagrama de estados
Dezembro | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb
| Diagrama de sequencia Mockups |  |  | Mockups |  |  | Dossier de organização do grupo |  | Entrega 3 |  | Poster (ingles)
Janeiro | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex | Sáb | Dom | Seg | Ter | Qua | Qui | Sex
[6 empty] | Entrega 4 |  |  |  |  | Dossier de organização do grupo |  | Entrega 5 |  |  | Defesa |  |  |  | Defesa

## E - Sprint 1
Release Goal: | Especificações
Start date: | 2022-09-19
End date: | 2022-09-23
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done | Ideia do projeto | 2h | Todos | 2h | Task
2 | MUST | Done | Contextualização (documento) | 4h | Gonçalo | 4h | Task
3 | MUST | Done | Preparar repositórios (GitHub) | 30min | João | 30min | Task

## E - Sprint 2
Release Goal: | Especificações
Start date: | 2022-09-24
End date: | 2022-09-30
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done | Brainstorm e estabelecimento das funcionalidades | 4h | Todos | 4h | Task
2 | MUST | Done | Levantamento de requisitos funcionais e não funcionais | 4h | Pedro e João | 4h | Task
3 | MUST | Done | Cliente e Utilizadores (contextualizacão) | 1h | João | 1h | Task

## E - Sprint 3
Release Goal: | Especificações
Start date: | 2022-10-01
End date: | 2022-10-07
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done | Mockups | 6h | João e Gonçalo | 6h | Task
2 | MUST | Done | Beneficios e Impacto (contextualização) | 1h | João | 30min | Task
3 | MUST | Done | Stakeholders | 1h | Pedro | 30min | Task

## E - Sprint 4
Release Goal: | Especificações
Start date: | 2022-10-08
End date: | 2022-10-14
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done | Modelo Canvas | 2h | João | 2h | Task
2 | MUST | Done | Cronograma | 3h | Gonçalo | 3h | Task
3 | MUST | Done | Sistema de avaliação | 1h | Pedro | 30min | Task
4 | MUST | Done | Atas | 1h | Pedro | 30min | Task

## E - Sprint 5
Release Goal: | Especificações
Start date: | 2022-10-15
End date: | 2022-10-21
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done | Product backlog | 4h | Todos | 4h | Task
2 | MUST | Done | Tutoriais (hardware e software) | 8h | Todos | 8h | Task

## E - Sprint 6
Release Goal: | Especificações
Start date: | 2022-10-22
End date: | 2022-10-28
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done | Diagrama de componentes | 2h30 | Pedro e Gonçalo | 1h | Task
2 | MUST | Done | Diagrama de casos de uso | 2h30 | João e Gonçalo | 2h | Task
3 | MUST | Done | Diagrama de classes | 2h30 | Gonçalo e Pedro | 2h | Task
4 | MUST | Done | Diagrama de BPMN | 2h | Pedro e João | 2h | Task
5 | MUST | Done | Diagrama de Atividades | 2h | João e Gonçalo | 2h | Task
6 | MUST | Done | Diagrama de Estados | 2h | João e Pedro | 2h | Task

## E - Sprint 7
Release Goal: | Especificações
Start date: | 2022-10-29
End date: | 2022-11-04
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done | Diagrama Entidade-Relação | 4h | João e Pedro | 4h | Task
2 | MUST | Done | Desenvolvimento da base de dados | 2h | João e Gonçalo | 2h | Task
3 | Must | Done | Testes base de dados | 3h | Todos | 3h | Task

## I - Sprint 1
Release Goal: | Implementação
Start date: | 2022-11-05
End date: | 2022-11-11
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 2
Release Goal: | Implementação
Start date: | 2022-11-12
End date: | 2022-11-18
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 3
Release Goal: | Implementação
Start date: | 2022-11-19
End date: | 2022-11-25
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 4
Release Goal: | Implementação
Start date: | 2022-11-26
End date: | 2022-12-02
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 5
Release Goal: | Implementação
Start date: | 2022-12-03
End date: | 2022-12-09
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 6
Release Goal: | Implementação
Start date: | 2022-12-10
End date: | 2022-12-16
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 7
Release Goal: | Implementação
Start date: | 2022-12-17
End date: | 2022-12-23
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 8
Release Goal: | Implementação
Start date: | 2022-12-24
End date: | 2022-12-30
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 9
Release Goal: | Implementação
Start date: | 2022-12-31
End date: | 2023-01-06
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task

## I - Sprint 10
Release Goal: | Implementação
Start date: | 2022-12-07
End date: | 2023-01-13
ID | Priority | Status | Task | Estimate (hours) | Who | Real time (hours) | Type
1 | MUST | Done |  |  |  |  | Task
2 | MUST | Done |  |  |  |  | Task
3 | Must | Done |  |  |  |  | Task